## Customer sheet
Customer part
[your logo here]
New Product Development Plan Template
Product |  | xxx |  | Date | 2023-01-01
Short description |  | xxx |  | Version | V1.0
|  |  |  | Released | N
Phase 1 |  | Specifications
|  | Deliverables: | Specifications defining the products with sufficient details to proceed to design phases
|  | Prerequisite: | Review and discuss requirements with project owner
|  | Responsible party | Details | Deliverables | Status
| 1 |  | External design (ID design - product outlook) | ID Design
| 1 |  | Product main dimensions (outside) | Drawings
| 1 |  | User interface | UI Document
| 1 |  | User manual | User Manual
| 1 |  | Performance requirements | Performance Requirement document
| 1 |  | Evaluate project main risk review from product development to production | Risk Analysis document
| 1 |  | Export countries and compliance requirements | Compliance Requirement document
Phase 2 |  | Feasibility / Proof of Concept
|  | Deliverables: | Design files (hardware and electronic), proof of concept, architecture, and theorical validation
|  | Prerequisite: | Specification completed and final
|  | Responsible party | Details | Deliverables | Status
| 1 |  | Feasibility study (engineering, testing, research) | Feasibility Report
| 1 |  | Mechanical structure | Design files
| 1 |  | Electronic architecture, schematic, check datasheets | Schematic
| 1 |  | Software/Firmware architecture | SW/FW Flowchart
| 1 |  | App architecture (mobile) | App Architecture Folder
| 1 |  | Product rendering and vitual video (marketing) | Pictures & video
| 1 |  | Solutions selection (materials, components, technologies) - Research studies | BOM
| 1 |  | Initial BOM (Bill of Material) based on main components | BOM
| 1 |  | Sourcing of main components (BOM), including samples | BOM
| 1 |  | Initial cost estimate (prototype, tooling, and production) | BOM
| 1 |  | Proof of concept prototype(s) | Test Report
| 1 |  | Product reliability test plan | Reliability plan
| 1 |  | Product compliance test plan estimate | Compliance plan
| 1 |  | Project risk analysis updated | Risk Document
| 1 |  | Updated project cost and timeline | NPD plan
| 1 |  | Patent research (for similar products) | Research Report
Phase 3 |  | Engineering Design and Prototypes | (there might be multiple prototype phases)
|  | Deliverables: | Functional prototype same as production, and functional test report
|  | Prerequisite: | Feasibility completed
|  | Responsible party | Details | Deliverables | Status
| 1 |  | Order parts | BOM
| 1 |  | DFx analysis and optimization (Design for Manufacturing, for Cost, for quality) | DFx Report
| 1 |  | PCBA layout | Gerber files
| 1 |  | Firmware development | Source code
| 1 |  | Software development and debug | Source code
| 1 |  | Full BOM with cost breakdown | BOM
| 1 |  | Assembly | Assembly Report
| 1 |  | Functional testing and reporting | Test report
| 1 |  | Prototype shipment and users/decision-maker approval | Product Checklist
| 1 |  | Rework based on test results
| 1 |  | Update cost estimate (tooling and production) | BOM
| 1 |  | Project risk analysis updated | Risk document
| 1 |  | Adjusted project cost and timeline | NPD plan
Phase 4 |  | Tooling and Other Preparations
|  | Deliverables: | Final prototype from tooling, reliability and compliance approval to start mass production
|  | Prerequisite: | Functional and approved prototype
|  | Responsible party | Details | Deliverables | Status
| 1 |  | Define parts requirements (acceptance) for existing and custom made
| 1 |  | Set tooling contract with suppliers (ownership, ability to retrieve...) | Contracts
| 1 |  | Order tools and follow up | BOM
| 1 |  | Order parts, including risk buy for long leadtime | BOM
| 1 |  | Confirm suppliers production yields (production pass rate) | BOM
| 1 |  | Validate and confirm samples from tooling | Sample review
| 1 |  | Assemble and functional test final prototype | Assembly review
| 1 |  | Packaging definition and artwork | Design files
| 1 |  | Packaging sample | Sample review
| 1 |  | Reliability tests (humidity, temperature, vibration, droptest,…) | Test report
| 1 |  | Compliance tests (FCC, CE, PROP65, UL,…) including design adjustments as needed | Certifications
| 1 |  | Ship final product to users/early customers for approval
| 1 |  | User testing (real cases with end users)
| 1 |  | Project risk analysis updated with FMEA | FMEA
| 1 |  | Identify production risks (components, supplier, assembly…) | Risk document
| 1 |  | Update cost estimate and timeline (production) | NPD plan
Phase 5 |  | Pre-Production Preparations
|  | Deliverables: | First production batch (based on production process) to ensure mass production can start
|  | Prerequisite: | Tooling approved, compliance and reliability testing passed
|  | Responsible party | Details | Deliverables | Status
| 1 |  | Set contract with major suppliers | Contracts
| 1 |  | Define assembly procedures | SOP
| 1 |  | Define quality plan (Incoming QC, Outgoing QC, In-Process QC…) & targets | Quality plan
| 1 |  | Define work instructions | SOPs/WIs
| 1 |  | Make tooling and jigs for assembly or quality control | Jig list
| 1 |  | Order material for the Pre-Production pilot run (including risk buy) | BOM
| 1 |  | Small P-P pilot run (about 5% of mass production batch) | PP report
| 1 |  | Pre-production review on process and material | PP report
Phase 6 |  | Mass Production
|  | Deliverables: | Mass production of final products
|  | Prerequisite: | Pre-production run approved with yield over 90% (assembly first-pass rate)
|  | Responsible party | Details | Deliverables | Status
| 1 |  | Order material | IQC reports
| 1 |  | Assembly
| 1 |  | Perform Outgoing QC inspection and report | OQC report
| 1 |  | Ship products out | Products